## Sheet1
Risk | Likelihood | Impact | Mitigation
Delays in fit-out | High | High | Add 1-week buffer, daily check-ins
Budget overruns | Medium | High | 10% contingency included
Staff turnover pre-launch | Medium | Medium | Offer bonuses, early contracts
Permit/license delays | Low | High | Start permit process early